## Sheet1
| 6th-12th Jan 2020 | [6 empty] | 13th-19th Jan 2020 | [6 empty] | 20th-26th Jan 2020 | [6 empty] | 27th Jan-2nd Feb 2020 | [6 empty] | 3rd-9th Feb 2020 | [6 empty] | 10th-14th Feb 2020
| M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | Tutorials
Activity | [40 empty] | Samia
Research: SQL/MongoDB, Matplotlib, rpy2, Flask, Django, Mass Spec Relativity, AWS | [40 empty] | Tong | bar: 6th-12th Jan 2020 M to 27th Jan-2nd Feb 2020 S
Data mining for kinases | [40 empty] | Solomon | bar: 6th-12th Jan 2020 F to 13th-19th Jan 2020 S
Abhi | bar: 6th-12th Jan 2020 F to 13th-19th Jan 2020 S
Dat Mining for Phosphosites | [40 empty] | Arun | bar: 6th-12th Jan 2020 F to 13th-19th Jan 2020 S
Everyone | bar: 6th-12th Jan 2020 F to 13th-19th Jan 2020 S
Data mining for inhibitors | bar: 6th-12th Jan 2020 F to 13th-19th Jan 2020 S
Constructing databases | bar: 20th-26th Jan 2020 M to 27th Jan-2nd Feb 2020 W
Data visualisation, Analysis | bar: 20th-26th Jan 2020 M to 3rd-9th Feb 2020 F
Website, Integration: | bar: 20th-26th Jan 2020 M to 3rd-9th Feb 2020 F
Deployment | bar: 3rd-9th Feb 2020 M to 3rd-9th Feb 2020 F
Debugging | bar: 27th Jan-2nd Feb 2020 T to 10th-14th Feb 2020 M
Documentation and Personal Write Ups | bar: 3rd-9th Feb 2020 W to 10th-14th Feb 2020 W
Presentation | bar: 3rd-9th Feb 2020 W to 10th-14th Feb 2020 W